## Product Backlog
Story ID | Epic | As a [Role] | I want to [Action] | So that [Benefit/Value] | Acceptance Criteria | Priority (MoSCoW) | Story Points | Sprint/Iteration
US-001 | Authentication | Teaching Assistant (TA) | register an account with my student ID, name, email, and password | I can access the recruitment system and apply for TA positions | 1. System validates student ID format (8-digit BUPT ID). 2. Password must be ≥8 chars with at least one letter and one digit. 3. Duplicate student ID is rejected with a clear error message. 4. Verify that application data is successfully stored and can be retrieved by the Module Organiser. | Must Have | 3 | 1
US-002 | Authentication | Module Organiser (MO) | log in with my staff credentials | I can manage job postings and review applicants securely | 1. MO can log in using pre-registered staff ID and password. 2. Invalid credentials display an appropriate error message. 3. Session state is maintained after successful login. | Must Have | 2 | 1
US-003 | Authentication | Admin | log in with administrator credentials | I can oversee all recruitment activities and manage system-wide data | 1. Admin login uses a separate credential set stored in config. 2. Admin dashboard is displayed upon successful login. 3. Unauthorised access attempts are logged. | Must Have | 2 | 1
US-004 | Job Management | Module Organiser (MO) | post a new TA job with module name, required skills, hours/week, and semester | qualified TAs can discover and apply for my module's open positions | 1. Job posting form includes: module name, description, required skills (multi-select), hours/week, deadline. 2. Posted job is saved to jobs.json and appears in the TA job listing. 3. MO receives a confirmation message upon successful posting. | Must Have | 5 | 1
US-005 | Job Management | Teaching Assistant (TA) | browse and search a list of all available TA positions | I can find positions that match my skills and availability | 1. Job listing displays module name, MO name, hours/week, and deadline. 2. TA can filter jobs by keyword or skill tag. 3. Jobs past their deadline are not displayed. | Must Have | 5 | 1
US-006 | Application | Teaching Assistant (TA) | apply for a TA position by submitting my profile and a brief cover statement | my application is recorded and visible to the Module Organiser | 1. TA selects a job and clicks "Apply". 2. Application record (TA ID, Job ID, timestamp, cover statement) is saved to applications.json. 3. Duplicate applications for the same job are prevented. | Must Have | 5 | 1
US-007 | Profile | Teaching Assistant (TA) | create and edit my applicant profile including skills, GPA, and availability | Module Organisers can evaluate my qualifications accurately | 1. Profile fields: name, student ID, email, skills (tags), GPA, year of study, availability (hours/week). 2. Profile data is saved to ta_profiles.json. 3. TA can update profile at any time; changes are immediately persisted. | Must Have | 3 | 1
US-008 | Application | Teaching Assistant (TA) | check the current status of all my submitted applications | I know whether I have been shortlisted, accepted, or rejected | 1. Status page lists all applications with current status (Submitted, Under Review, Accepted, Rejected). 2. Status updates reflect changes made by the MO in real-time (on page refresh). | Must Have | 3 | 2
US-009 | Selection | Module Organiser (MO) | view all applications for my posted job and accept or reject candidates | I can efficiently select the most suitable TAs for my module | 1. MO sees a list of applicants with profile summaries for each job. 2. MO can change application status to Accepted or Rejected. 3. Status changes are saved to applications.json immediately. | Must Have | 5 | 2
US-010 | Profile | Teaching Assistant (TA) | upload my CV as a file attachment to my profile | Module Organisers have access to my full qualifications | 1. System accepts PDF and DOCX files up to 2MB. 2. File is stored in a designated uploads directory. 3. File path is linked in the TA profile JSON. | Should Have | 3 | 2
US-011 | Workload | Admin | view an overview dashboard showing each TA's total assigned hours across all accepted positions | I can ensure no TA is over-committed and workload is fairly distributed | 1. Dashboard displays TA name, total accepted hours, and a list of assigned modules. 2. TAs exceeding 20 hours/week are flagged with a visual warning. 3. Data is aggregated from applications.json and jobs.json. | Should Have | 5 | 2
US-012 | AI Matching | Teaching Assistant (TA) | see a "match score" showing how well my skills align with each job posting | I can prioritise applications for roles where I am most qualified | 1. Match score (0–100%) is calculated based on skill overlap between TA profile and job requirements. 2. Score is displayed next to each job listing. 3. Algorithm is explainable: tooltip shows matched and missing skills. | Should Have | 8 | 3
US-013 | AI Matching | Module Organiser (MO) | see applicants ranked by an AI-generated suitability score | I can quickly identify the strongest candidates without manually comparing profiles | 1. Applicants are sorted by a composite score (skill match + GPA + availability fit). 2. MO can view breakdown of each score component. 3. AI recommendation is clearly labelled as a suggestion, not a decision. | Should Have | 8 | 3
US-014 | AI Skills | Teaching Assistant (TA) | receive suggestions on skills I am missing for jobs I am interested in | I can develop relevant skills to improve my future applications | 1. System identifies skill gaps between TA profile and target job requirements. 2. Missing skills are displayed in a "Skills to Develop" panel. 3. Suggestions include at least 2 actionable learning recommendations. | Could Have | 5 | 3
US-015 | AI Workload | Admin | receive AI-powered suggestions for balanced workload distribution when multiple TAs are eligible for the same role | recruitment decisions consider fairness and prevent burnout | 1. System suggests optimal TA-to-job assignments minimising max individual hours. 2. Admin can accept, modify, or reject recommendations. 3. Algorithm explanation is provided (e.g., "TA X has 8 free hours; TA Y has 2"). | Could Have | 8 | 4
US-016 | Notification | Teaching Assistant (TA) | receive in-app notifications when my application status changes | I stay informed without having to repeatedly check the system | 1. Notification badge appears on the TA dashboard when a status changes. 2. Notification log shows timestamp and new status. 3. Notifications are stored in notifications.json. | Could Have | 5 | 4
US-017 | Reporting | Admin | export recruitment reports (e.g., total applications per module, acceptance rate) as a CSV file | I can share recruitment analytics with school management | 1. Report includes: module name, total applicants, accepted count, rejection count. 2. CSV file is generated and downloadable. 3. Report covers a user-specified date range. | Could Have | 5 | 4
US-018 | Job Management | Module Organiser (MO) | edit or close an existing job posting | I can correct errors or stop accepting applications after positions are filled | 1. MO can update job details (description, skills, deadline). 2. MO can set status to "Closed"; closed jobs no longer appear in TA listings. 3. Existing applications are preserved when a job is edited or closed. | Should Have | 3 | 2
US-019 | Invigilation | Admin | post invigilation tasks and assign available TAs to exam sessions | exam invigilation is staffed efficiently alongside regular TA duties | 1. Invigilation task includes: exam name, date/time, location, required TAs. 2. Admin can assign TAs who have confirmed availability. 3. Assigned invigilation hours are added to TA workload totals. | Could Have | 5 | 4
US-020 | Authentication | All Users | reset my password via a security question | I can regain access to my account if I forget my password | 1. User provides student/staff ID and answers a security question set during registration. 2. If correct, user is prompted to set a new password. 3. New password is validated and saved. | Won't Have (this time) | 3 | 4
US-021 | AI Matching | Module Organiser (MO) | view the breakdown of an applicant's suitability score | I can understand why a candidate was ranked highly | 1. Verify MO can view score components: skill match, GPA, and availability fit. 2. Verify data is displayed in a clear, readable format (e.g., breakdown panel). | Should Have | 3 | 3

## Legend
Priority | Meaning
Must Have | Essential for the MVP; system cannot function without it.
Should Have | Important but not critical; included if time permits.
Could Have | Desirable enhancements; deferred if needed.
Won't Have (this time) | Out of scope for this release cycle.